## Design Scope
Discipline | Scope Item | Assumptions / Clarifications | Exclusions | Arup Comments | Accepted
Technical Governance and Assurance | Feasibility Scope Definition | Work to date to agree scope and contract |  | Arup Comments+E4:E121
| Programme | Submitted on a monthly basis
| RFI/TQs | Submitted via Aconex
| Task Information Delivery Plan (TIDP) | Submitted bi-weekly via ProjectWise
| Weekly Design Progress Meeting | Attendance by PM, DM/DC and relevant discipline leads (can vary depending on focus)
Arup Internal Coordination Meetings
Constructability Workshops (in person)
BIM Kick Off Meeting
Monthly BIM Coordination Meeting
Arup Internal BIM Management
Bi-weekly Commercial Meeting
| Construction methodology optimisation and optioneering | Includes all disciplines - e.g. above ground or tunnelling solution for feed pipe. |  | This will be high-level assessment - proper optimisation will fit better in later FEL stages | Agreed. Main item here is to decide on the most appropriate solution and highlight risks and opportunities for design development.
| Update UU/Jacobs cost estimate for 40% FTFT option |  |  |  | CHANGE: Exclusion removed. Arup to provide full cost estimate. Estimating class specified as Class 4, but figures are not the Mean Pricing Accuracy Range.
| Produce cost estimate for 60% FTFT option |  |  | Equivalent to AACE Class 4 (-30 / +50) | CHANGE: Exclusion removed. Arup to provide full cost estimate. Estimating class specified as Class 4, but figures are not the Mean Pricing Accuracy Range.
| Produce cost estimate for optimised 60% FTFT option |  |  | Equivalent to AACE Class 4 (-30 / +50) | CHANGE: Exclusion removed. Arup to provide full cost estimate. Estimating class specified as Class 4, but figures are not the Mean Pricing Accuracy Range.
| Create cost comparison between two options | To include design costs and supply, install and integration of key packages |  | Equivalent to AACE Class 4 (-30 / +50) | CHANGE: Exclusion removed. Arup to provide full cost estimate. Estimating class specified as Class 4, but figures are not the Mean Pricing Accuracy Range.
Single Solution Paper
TAG Review Presentation
| Attendance and presentation at TAG review | Arup will present the SSP at the TAG review
40% Option - AMP9 Requirements
Civil | PCI Review and Gap Analysis | Includes Davyhulme PCI folder and all information issued by Enterprise (including all CDPs & Jacobs/SST/ASG) to inform the design
| ASP4 Feed Main Road Crossings | Assume 2 No.
| ASP4 Feed Main Storm Channel Crossing | Assume 1 No. from ASP2 outlet Chamber to ASP4 Feed Pumping Station
| Ducting and Drawpit Layout |  |  | High-level layout on site plan (not detail of internals ) | Agreed. High level plan only.
Structural | PCI Review and Gap Analysis | Includes Davyhulme PCI folder and all information issued by Enterprise (including all CDPs & Jacobs/SST/ASG) to inform the design
| Assessment of existing ASP1 Structure | Intention is to reuse the base slab and piles of the existing structure and demolish the walls (except wall adjacent to existing OCUs)
Survey Specification for ASP1 Foundation and Piles
| Assessment of existing ASP1 wall adjacent to OCUs | Wall to act as retaining wall to protect existing OCUs
ASP2 Outlet Chamber
ASP4 Feed Pumping Station
Fine Screens Lanes
ASP4 Feed Distribution Chamber & Anoxic Recycle Chamber
| ASP4 Structure |  |  | What are the limits on this / what is supplied as the MBR package? | MBR supplier engagement to date has been shared with Arup. This will inform this scope item.
MBR Lift & MRAS Pumping Station
| Membrane Tank Structure | Includes Feed Channel, Overflow Weirs, MBR Trains
MRAS Dearation Tank
MBR Permeate & Backpulse Pumps slab
| Permeate Tank | Assume FRC but optioneering will need carrying out on construction methodology
SAS Draw Off Pump slab
| SAS Buffer Tank | Assume FRC but optioneering will need carrying out on construction methodology
SAS transfer pumping slab
| Chemical dosing slabs | Assume slabs for Sodium Hypochlorite & Citric Acid storage and dosing pump kiosk
| Pipe Supports | For all pipes not supported off new / existing structures. |  | Normally developed at detailed design | High level quantity and size estimate only to inform cost estimate.
Geotechnical | PCI Review and Gap Analysis | Includes Davyhulme PCI folder and all information issued by Enterprise (including all CDPs & Jacobs/SST/ASG) to inform the design
| Digitisation of existing GI |  |  | Is the existing GI hand written field-notes; or PDF taken from a legacy UU data system? | Existing GI can be found in the PCI folder. Arup P-Fix team has undertaken digitisation of relevant GI data to date. Please advise if further digitisation is required.
| GI specification | Includes attendance for Arup team |  | Normally part of later FEL stages. If Arup team attending does this mean specification and the GI survey itself? | No reason not to carry out GI at this stage considering the level of progress on the site layout. Keep production of specification in there and allow for required Arup attendance.
| Geoenvironmental Risk Assessment | Assume required for planning purposes. |  | From PCI only – full RA would be in later FEL stages. Planning activities not normally integrated in Feasibility but can run in parallel - are they part of the TAG review? | Agreed - to be removed from scope. This will need capturing in the Outline Design scope.
Assessment of existing piled foundations
Process | PCI Review and Gap Analysis | Includes Davyhulme PCI folder and all information issued by Enterprise (including Jacobs/SST/ASG) to inform the design
| Validation of solution against Mass Balance | Validation against design horizon and population increase, WINEP drivers and operational requirements |  | We understood this to be Jacobs' scope - are we providing a check? | Yes, validation check as agreed in meeting with UU/Jacobs 18/05/2026
| Validate Hydraulic Model | Validation against design horizon and population increase, WINEP drivers and operational requirements |  | Hydraulic model of feed (rising) and return (gravity) mains - not the detail around the MBR | Agreed as per meeting 18/05/2026.
| Validate Process Sizing | Validation against design horizon and population increase, WINEP drivers and operational requirements |  | We understood this to be Jacobs' scope - are we providing a check? | Yes, validation check as agreed in meeting with UU/Jacobs 18/05/2026
| Validate Chemical Dosing | For Sodium hypochlorite, citric acid and ferric. Validation against design horizon and population increase, WINEP drivers and operational requirements |  | We understood this to be Jacobs' scope - are we providing a check? | Yes, validation check as agreed in meeting with UU/Jacobs 18/05/2026
| Specifications for verification sampling | To be coordinated with Enterprise and UU Ops |  | Part of detailed design scope? | Disagree. Need to highlight requirement for sampling at this stage to inform future stages.
Mechanical | PCI Review and Gap Analysis | Includes Davyhulme PCI folder and all information issued by Enterprise (including all CDPs & Jacobs/SST/ASG) to inform the design
ASP4 Feed PS Pumps
| ASP4 Feed Main | Assume pipe route will be above ground (storm channel and road crossings captured in civils section) |  | Is above ground an aspiration or a constraint? | Currently no indication that above ground is mandatory. Route to be determined by Arup in accordance with site constraints, UU asset standards and any other relevant standards / guidance to provide a robust and compliant solution.
| Fine Screens | Assume fine screens only
| Above Ground Pipework | All gravity and pressure pipework relating to ASP4. Feed Main and Return Main to ASP2 are captured separately |  | How much (if any) is part of the MBR vendor package? | To be confirmed following Arup review of the supplier engagement to date, and to be agreed as part of this feasibility scope. Encourage Arup supplier engagement to define this. This will be assisted by the Murphy procurement team.
| Anoxic Recycle Pumps | Includes associated pipework
MBR Mechanical Design
| MBR Permeate & Backpulse Pumps | Includes associated pipework
| SAS Pumps (draw off) | Includes associated pipework
| SAS Pumps (transfer) | Includes associated pipework
Blowers Kiosk
| Blowers | Includes associated pipework |  | Blower air rate specification from MBR vendor or Jacobs? | To be confirmed following Arup review of the supplier engagement to date, and to be agreed as part of this feasibility scope.
| Dosing Pumps | Assume pumps and associated pipework for Sodium Hypochlorite & Citric Acid storage and dosing
| Dosing Kiosk | Assume 1 No. Kiosk for both Sodium Hypochlorite & Citric Acid dosing
| MBR permeate Pipeline | Return line from Permeate Tank to ASP2
| Supplier Engagement for Mechanical Equipment |  |  | Supplier engagement not normally part of Feasibility and better suited to later FEL a stages. | Supplier engagement will be required to inform cost estimate and single solution.
Electrical & ICA | PCI Review and Gap Analysis | Includes Davyhulme PCI folder and all information issued by Enterprise (including all CDPs & Jacobs/SST/ASG) to inform the design
Telemetry Survey specification
ICA Surveys specification
Power / Load Assessment
Transformer
MCC
Cable route layout
60% Option - AMP10 Storm Spill Requirements
Civil | ASP4 Feed Main Road Crossings | Assume 2 No.
| ASP4 Feed Main Storm Channel Crossing | Assume 1 No.
| Hydraulic assessment of existing outfall | Outfall from ASP2 TO Manchester Shipping Canal
Ducting and Drawpit Layout
Structural | ASP2 Outlet Chamber
ASP4 Feed Pumping Station
Fine Screens Lanes
ASP4 Feed Distribution Chamber & Anoxic Recycle Chamber
ASP4 Structure
MBR Lift & MRAS Pumping Station
| Membrane Tank Structure | Includes Feed Channel, Overflow Weirs, MBR Trains
MRAS Dearation Tank
MBR Permeate & Backpulse Pumps slab
| Permeate Tank | Assume FRC but optioneering will need carrying out on construction methodology
SAS Draw Off Pump slab
| SAS Buffer Tank | Assume FRC but optioneering will need carrying out on construction methodology
SAS transfer pumping slab
| Chemical dosing slabs | Assume slabs for Sodium Hypochlorite & Citric Acid storage and dosing pump kiosk
| Pipe Supports | For all pipes not supported off new / existing structures.
Geotechnical | Digitisation of existing GI
GI specification
| Geoenvironmental Risk Assessment | Assume required for planning purposes.
Process | Validation of solution against Mass Balance | Validation against design horizon and population increase, WINEP drivers and operational requirements
| Creation of Hydraulic Model | Creation of hydraulic model in accordance with design horizon and population increase, WINEP drivers and operational requirements |  |  | CHANGE: Creation of hydraulic model rather than validation of existing as agreed in the meeting held 18/05/2026
| Validate Process Sizing | Validation against design horizon and population increase, WINEP drivers and operational requirements
| Validate Chemical Dosing | For Sodium hypochlorite, citric acid and ferric. Validation against design horizon and population increase, WINEP drivers and operational requirements
Validation of the process design - Hydraulics
| Specifications for verification sampling | To be coordinated with Enterprise and UU Ops
Mechanical | ASP4 Feed PS Pump
| ASP4 Feed Main | Pipe route will be above ground
Fine Screens
| Above Ground Pipework | All gravity and pressure pipework relating to ASP4. Feed Main and Return Main to ASP2 are captured separately
| Anoxic Recycle Pumps | Includes associated pipework
MBR Mechanical Design
| MBR Permeate & Backpulse Pumps | Includes associated pipework
| SAS Pumps (draw off) | Includes associated pipework
| SAS Pumps (transfer) | Includes associated pipework
Blowers Kiosk
| Blowers | Includes associated pipework
| Dosing Pumps | Assume pumps and associated pipework for Sodium Hypochlorite & Citric Acid storage and dosing
| Dosing Kiosk | Assume 1 No. Kiosk for both Sodium Hypochlorite & Citric Acid dosing
| MBR permeate Pipeline | Return line from Permeate Tank to ASP2
Supplier Engagement for Mechanical Equipment
Electrical & ICA | Telemetry Survey specification
ICA Surveys specification
Power / Load Assessment
Transformer
MCC
Cable route layout
Optimised 60% Option - AMP10 Storm Spill Requirements
Civil | ASP4 Feed Main Road Crossings | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| ASP4 Feed Main Storm Channel Crossing | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Hydraulic assessment of existing outfall | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Ducting and Drawpit Layout | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
Structural | ASP2 Outlet Chamber | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| ASP4 Feed Pumping Station | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Fine Screens Lanes | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| ASP4 Feed Distribution Chamber & Anoxic Recycle Chamber | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| ASP4 Structure | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MBR Lift & MRAS Pumping Station | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Membrane Tank Structure | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MRAS Dearation Tank | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MBR Permeate & Backpulse Pumps slab | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Permeate Tank | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| SAS Draw Off Pump slab | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| SAS Buffer Tank | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| SAS transfer pumping slab | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Chemical dosing slabs | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Pipe Supports | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
Geotechnical | Digitisation of existing GI | Assume same as 60% option
| GI specification | Assume same as 60% option
| Geoenvironmental Risk Assessment | Assume same as 60% option
Process | Validation of solution against Mass Balance | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Creation of Hydraulic Model | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope. |  |  | CHANGE: Creation of hydraulic model rather than validation of existing as agreed in the meeting held 18/05/2026
| Validate Process Sizing | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Validate Chemical Dosing | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Validation of the process design - Hydraulics | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Specifications for verification sampling | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
Mechanical | ASP4 Feed PS Pump | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| ASP4 Feed Main | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Fine Screens | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Above Ground Pipework | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Anoxic Recycle Pumps | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MBR Mechanical Design | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MBR Permeate & Backpulse Pumps | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| SAS Pumps (draw off) | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| SAS Pumps (transfer) | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Blowers Kiosk | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Blowers | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Dosing Pumps | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Dosing Kiosk | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MBR permeate Pipeline | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Supplier Engagement for Mechanical Equipment | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
Electrical & ICA | Telemetry Survey specification | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| ICA Surveys specification | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Power / Load Assessment | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Transformer | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| MCC | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
| Cable route layout | Optimisation of 60% option to cover optimisation / efficiency items only. e.g. quantity of pipes, pumps, changes to structures etc. Include what is over and above 60% scope.
General / Other
Temporary Works | Temporary Works design |  | Temporary Works design excluded from scope